RESOLUTION NO. 2026-8.4
OF THE GOVERNING BODY OF

THE BOROUGH OF BLOOMINGDALE

RESOLUTION OF THE BOROUGH OF BLOOMINGDALE, COUNTY OF PASSAIC AND STATE OF NEW JERSEY AUTHORIZING CHANGE ORDER #2 FOR THE CONTRACT AWARDED TO MIKE FITZPATRICK CONTRACTORS, INC. FOR ANN STREET & ELM STREET WATER MAIN IMPROVEMENTS 

WHEREAS, the Borough of Bloomingdale and Mike Fitzpatrick Contractors, Inc., have entered into a contract in the amount of $629,693.00 for the water main improvement project via Resolution No. 2025-10.21; and,

WHEREAS, change order #1 in the amount of $39,885.23 was approved via Resolution No. 2026-6.8 and the new contract total is $669,578.23; and
WHEREAS, it has been further recommended by the Borough Engineer, Thomas A. Boorady of Darmofalski Engineering Associates, Inc., that additional changes to this contract are necessary & were unknown or unforeseen at the time of plan preparations. 

WHEREAS, change order #2 is outlined in memorandum dated August 7, 2026 submitted to Mayor & Council by the Borough Engineer. In summary of the memorandum, this change order provides for the installation of a modified valve assembly on Charles Street, including necessary excavation support and dewatering, to connect the new water main while improving long-term accessibility and maintenance of the Borough's water distribution system.
Non-Contract Work Items 









Additional Cost


Change Order #1






$ 39,885.23
Proposed Change Order #2




 +
$ 29,000.00
Total Net Change Order(s): $ 68,885.23





Percentage Increase:

10.94%
; and


WHEREAS, the original contract amount was $629,693.00; the amended contract amount based upon Change Order #1 and #2 is $698,578.23 which is a 10.94% increase from the original contract amount; and,
WHEREAS, in accordance with N.J.A.C. 5:30-11.3, the change orders have not caused the originally awarded contract price to be exceeded by more than 20 percent; and,
WHEREAS, the Borough Engineer, Thomas A. Boorady of Darmofalski Engineering Associates, Inc., has reviewed the change order and recommended to the Governing Body that it modify its agreement with and Mike Fitzpatrick Contractors, Inc., subject to the certification of funds, as a result of the above-referenced changes of condition which have occurred on the project and as detailed in the Borough Engineer’s email Memorandum, dated August 7, 2026; and,

WHEREAS, Borough Chief Financial Officer has certified the funds as evidenced in the annexed certification; and,


NOW, THEREFORE, BE IT RESOLVED by the Governing Body of the Borough of Bloomingdale, in the County of Passaic and State of New Jersey, that Change Order #2 is hereby approved in the contract between the Borough of Bloomingdale and Mike Fitzpatrick Contractors, Inc. as follows:

Original Contract


 $ 629,693.00

Change Order #1


 $  39,885.23

Change Order #2


 $   29,000.00

New Contract Total:

            $ 698,578.23





Increase 10.94%
This Resolution will take effect immediately upon approval and certification of funds.
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